## Dashboard Data (hidden)
ProjectID | dType | GEType | TID | Dependency | Dependents | StartConstrain | EndConstrain | TIL | SS | TaskIcon | WBS | Task | Priority | Status | Resource | ResourceCost | BSD | BED | BD | ESD | EED | ED | WBSPredecessors | WBSSuccessors | Work | Done | PercentageCompleted | ASD | AED | AD | BCS | ECS | ACS | Notes | Custom 1 | Custom 2 | Custom 3 | Custom 4 | Custom 5 | Custom 6 | Custom 7 | Custom 8 | Custom 9 | Custom 10 | Custom 11 | Custom 12 | Custom 13 | Custom 14 | Custom 15 | Custom 16 | Custom 17 | Custom 18 | Custom 19 | Custom 20 | LC | ProjectFilter
1 | MP | T | 1 |  |  |  |  | 0 |  | u | 1 | PRE PURCHASE STAGE | NORMAL | Completed | [5 empty] | 2022-04-18 | 2022-04-18 | 0 |  |  |  | 100 | 1 | [28 empty] | #REF!
1 | M | M | 51 |  |  |  |  | 1 |  | u | 1.1 | Development Site identified (3 Apple Flat Rd, Alligator Creek) | NORMAL | Completed | [5 empty] | 2022-05-01 | 2022-04-18 | 0 |  |  |  | 100 | 1 | [6 empty] | 3 Apple Flat Rd, Alligator Creek | [21 empty] | #REF!
1 | MP | T | 2 |  |  |  |  | 0 |  | u | 2 | NEGOTIATING CONTRACTS & PURCHASING | NORMAL | Overdue | [5 empty] | 2022-03-07 | 2022-04-11 | 1 |  |  |  | 0 | 0.33333 | 2022-04-12 | 2022-04-12 |  |  | 25000 | 5000 | [22 empty] | #REF!
1 | SP | T | 52 |  |  |  |  | 1 |  | u | 2.1 | PRIOR TO EXECUTION STAGE | NORMAL | Completed | [5 empty] | 2022-03-07 | 2022-04-11 | 0 |  |  |  | 100 | 1 | 2022-04-12 | 2022-04-12 | [26 empty] | #REF!
1 | M | M | 34 |  |  |  |  | 2 |  | u | 2.1.1 | Form 6 - Enlist Buyers Agent (Ben Waugh) | NORMAL | Completed | [5 empty] | 2022-04-11 | 2022-04-11 | 0 |  |  |  | 100 | 1 | [6 empty] | Ben Waugh | [21 empty] | #REF!
1 | M | M | 35 |  |  |  |  | 2 |  | u | 2.1.2 | Sign Contract | NORMAL | Completed | [5 empty] | 2022-04-11 | 2022-04-11 | 0 |  |  |  | 100 | 1 | 2022-04-12 | 2022-04-12 | 0 | [25 empty] | #REF!
1 | M | M | 36 |  |  |  |  | 2 |  | u | 2.1.3 | Sign Contract | NORMAL | Completed | [5 empty] | 2022-03-07 | 2022-03-07 | 0 |  |  |  | 100 | 1 | [6 empty] | Use QPLG, Yasmin Parker | [21 empty] | #REF!
1 | M | M | 37 |  | 45¦46¦ |  |  | 2 |  | u | 2.1.4 | Finalise Contract (both sides signed and accepted) agreed $593,000 | NORMAL | Completed | [5 empty] | 2022-03-11 | 2022-03-11 | 0 |  |  |  | 100 | 1 | [6 empty] | Agreed price $593K Contract is now binding but subject to key conditions being met | [21 empty] | #REF!
1 | SP | T | 53 |  |  |  |  | 1 |  | u | 2.2 | AFTER CONTRACT EXECUTED STAGE (Contract is subject to key conditions) | NORMAL | Completed | [5 empty] | 2022-03-14 | 2022-03-14 | 0 |  |  |  | 100 | 1 |  |  |  |  | 5000 | 5000 | [22 empty] | #REF!
1 | M | M | 45 | 37_FS_2¦ |  | 44634 |  | 2 |  | u | 2.2.1 | Pay $5K Deposit (within 2D of contract date) | NORMAL | Completed | [5 empty] | 2022-03-14 | 2022-03-14 | 0 |  |  |  | 100 | 1 |  |  |  |  | 5000 | 5000 | Don't forget to pay your $5K deposit (within 2 days of contract date) | [21 empty] | #REF!
1 | M | M | 46 | 37_FS_28¦ |  | 44660 |  | 1 |  | u | 2.3 | Engage Town Planner (straight after contract date) | NORMAL | Completed | [5 empty] | 2022-04-09 | 2022-04-09 | 0 |  |  |  | 100 | 1 | [6 empty] | Before 28 days is up get your building and pest done. (just to make sure no structural building issues or live termites). Twin Cities Bldg and Pest (Phone No: 07 4723 2770) - | [21 empty] | #REF!
1 | M | M | 44 |  |  |  |  | 1 |  | u | 2.4 | Complete Building Pest Inspection (before 28D) | NORMAL | Overdue | [5 empty] | 2022-03-16 | 2022-03-16 | 0 |  |  |  | 0 | 0 | [6 empty] | Use Twin Cities Bldg and Pest Ph: 07 4723 2770. Make sure no structural building issues or live termites. | [21 empty] | #REF!
1 | M | M | 43 |  |  |  |  | 1 |  | u | 2.5 | Advise 'unconditional' to Solicitor | NORMAL | Overdue | [5 empty] | 2022-03-18 | 2022-03-18 | 0 |  |  |  | 0 | 0 | [6 empty] | This means all checks are done and MITR happy to proceed with the deal and the contract terms are now satisfied. | [21 empty] | #REF!
1 | M | M | 42 |  |  |  |  | 1 |  | u | 2.6 | Pay $20K balance (within 35D of contract date) | NORMAL | Overdue | [5 empty] | 2022-03-17 | 2022-03-17 | 0 |  |  |  | 0 | 0 |  |  |  |  | 20000 | [23 empty] | #REF!
1 | M | M | 38 |  |  |  |  | 1 |  | u | 2.7 | Contract Unconditional within 35D (terms and condition satified) | NORMAL | Overdue | [5 empty] | 2022-03-07 | 2022-03-07 | 0 |  |  |  | 0 | 0 | [28 empty] | #REF!
1 | M | M | 40 |  |  |  |  | 1 |  | u | 2.8 | Pay Buyers Agent Commission | NORMAL | Overdue | [5 empty] | 2022-04-01 | 2022-04-01 | 0 |  |  |  | 0 | 0 | [28 empty] | #REF!
1 | C | T | 41 |  |  |  |  | 1 |  | u | 2.9 | Proceed with steps as recommended by Town Planner to DA into Council | NORMAL | Overdue | [5 empty] | 2022-03-07 | 2022-03-07 | 1 |  |  |  | 0 | 0 | [28 empty] | #REF!
1 | MP | T | 5 |  |  |  |  | 0 |  | u | 3 | DEVELOPMENT | NORMAL | Overdue | [5 empty] | 2022-03-07 | 2022-04-01 | 5 |  |  |  | 0 | 0 | [28 empty] | #REF!
1 | M | M | 49 |  |  |  |  | 1 |  | u | 3.1 | Submit DA to Council and Approval Stage | NORMAL | Overdue | [5 empty] | 2022-03-07 | 2022-03-07 | 0 |  |  |  | 0 | 0 | [28 empty] | #REF!
1 | M | M | 48 |  |  |  |  | 1 |  | u | 3.2 | Survey | NORMAL | Overdue | [5 empty] | 2022-03-08 | 2022-03-08 | 0 |  |  |  | 0 | 0 | [28 empty] | #REF!
1 | M | M | 47 |  |  |  |  | 1 |  | u | 3.3 | Power Application | NORMAL | Overdue | [5 empty] | 2022-04-01 | 2022-04-01 | 0 |  |  |  | 0 | 0 | [28 empty] | #REF!
1 | C | T | 3 |  |  |  |  | 1 |  | u | 3.4 | Operational Work Stage (if time permits or do after settlement) | NORMAL | Overdue | [5 empty] | 2022-03-14 | 2022-03-18 | 5 |  |  |  | 0 | 0 | [28 empty] | #REF!
1 | M | M | 50 |  |  |  |  | 1 |  | u | 3.5 | Settle Property as per Contract Timing | NORMAL | Overdue | [5 empty] | 2022-04-01 | 2022-04-01 | 0 |  |  |  | 0 | 0 | [28 empty] | #REF!
1 | MP | T | 7 |  |  |  |  | 0 |  | u | 4 | COMPLETION | NORMAL | Overdue | [5 empty] | 2022-04-01 | 2022-04-01 | 8 |  |  |  | 0 | 0 | [28 empty] | #REF!
1 | C | T | 15 |  |  |  |  | 1 |  | u | 4.1 | d | NORMAL | Overdue | [5 empty] | 2022-04-01 | 2022-04-01 | 1 |  |  |  | 0 | 0 | [28 empty] | #REF!
1 | C | T | 60 |  |  |  |  | 1 |  | u | 4.2 | d | NORMAL | Overdue | [5 empty] | 2022-04-01 | 2022-04-01 | 1 |  |  |  | 0 | 0 | [28 empty] | #REF!
1 | C | T | 59 |  |  |  |  | 1 |  | u | 4.3 | d | NORMAL | Overdue | [5 empty] | 2022-04-01 | 2022-04-01 | 1 |  |  |  | 0 | 0 | [28 empty] | #REF!
1 | C | T | 58 |  |  |  |  | 1 |  | u | 4.4 | d | NORMAL | Overdue | [5 empty] | 2022-04-01 | 2022-04-01 | 1 |  |  |  | 0 | 0 | [28 empty] | #REF!
1 | C | T | 57 |  |  |  |  | 1 |  | u | 4.5 | d | NORMAL | Overdue | [5 empty] | 2022-04-01 | 2022-04-01 | 1 |  |  |  | 0 | 0 | [28 empty] | #REF!
1 | C | T | 56 |  |  |  |  | 1 |  | u | 4.6 | d | NORMAL | Overdue | [5 empty] | 2022-04-01 | 2022-04-01 | 1 |  |  |  | 0 | 0 | [28 empty] | #REF!
1 | C | T | 55 |  |  |  |  | 1 |  | u | 4.7 | d | NORMAL | Overdue | [5 empty] | 2022-04-01 | 2022-04-01 | 1 |  |  |  | 0 | 0 | [28 empty] | #REF!
1 | C | T | 54 |  |  |  |  | 1 |  | u | 4.8 | d | NORMAL | Overdue | [5 empty] | 2022-04-01 | 2022-04-01 | 1 |  |  |  | 0 | 0 | [28 empty] | #REF!
2 | T | T | 1 |  |  |  |  | 0 |  | u | 1 | Type here or double click to edit in form | NORMAL | Overdue | [5 empty] | 2022-04-13 | 2022-04-26 | 10 |  |  |  | 0 | 0 | [28 empty] | #REF!
3 | MP | T | 1 |  |  |  |  | 0 |  | u | 1 | DESIGN | NORMAL | InProgress | [5 empty] | 2022-03-29 | 2022-06-09 | 65 |  |  |  | 0 | 0.57292 | [28 empty] | #REF!
3 | C | T | 2 |  |  |  |  | 1 |  | u | 1.1 | Selección zip codes y ciudades (Broadwar, Miami Dade, Cortéz, Fco Morazán) | NORMAL | Completed | Organization, CREATIVO |  |  |  |  | 2022-04-15 | 2022-04-15 | 1 |  |  |  | 100 | 1 | [28 empty] | #REF!
3 | M | M | 66 |  |  |  |  | 1 |  | u | 1.2 | dgdgdg | NORMAL | Overdue | [5 empty] | 2022-04-22 | 2022-04-22 | 0 |  |  |  | 0 | 0 | [28 empty] | #REF!
3 | C | T | 41 |  | 34¦ |  |  | 1 |  | u | 1.3 | Selección inicial de vecindarios en HON | NORMAL | Completed | [5 empty] | 2022-04-05 | 2022-04-05 | 1 |  |  |  | 100 | 1 | [28 empty] | #REF!
3 | C | T | 3 |  |  |  |  | 1 |  | u | 1.4 | Perfil preliminar de audicencias | NORMAL | Completed | MANAGER |  |  |  |  | 2022-04-15 | 2022-04-15 | 1 |  |  |  | 100 | 1 | [28 empty] | #REF!
3 | C | T | 43 |  |  |  |  | 1 |  | u | 1.5 | Encuestas preliminares HON 37 y EEUU 17 | NORMAL | Overdue | [5 empty] | 2022-04-03 | 2022-04-15 | 10 |  |  |  | 0 | 0.5 | [28 empty] | #REF!
3 | SP | T | 23 |  |  |  |  | 1 |  | u | 1.6 | Initiar field research -Equipo pequeño de calle para avanzada en ccios/rest en los zip codes del proyecto | NORMAL | Overdue | [5 empty] | 2022-03-29 | 2022-04-15 | 13 |  |  |  | 0 | 0.16667 | [28 empty] | #REF!
3 | C | T | 38 |  | 59¦ |  |  | 2 |  | u | 1.6.1 | Recorrido inicial de campo en EEUU - | NORMAL | Completed | MANAGER |  |  |  |  | 2022-04-11 | 2022-04-13 | 3 |  |  |  | 100 | 1 | [28 empty] | #REF!
3 | C | T | 59 | 38_FF_0¦ | 60¦ |  | 44664 | 2 |  | u | 1.6.2 | Agenda de visitas programadas | NORMAL | Overdue | MANAGER |  |  |  |  | 2022-04-11 | 2022-04-13 | 3 |  |  |  | 0 | 0 | [28 empty] | #REF!
3 | C | T | 65 |  |  |  |  | 2 |  | u | 1.6.3 | Agenda de visitas programadas | NORMAL | Overdue | MANAGER |  |  |  |  | 2022-03-29 | 2022-03-31 | 3 |  |  |  | 0 | 0 | [28 empty] | #REF!
3 | C | T | 60 | 59_FS_0¦ | 61¦ | 44665 |  | 2 |  | u | 1.6.4 | Producción materiales para entregar | NORMAL | Overdue | [5 empty] | 2022-04-14 | 2022-04-14 | 1 |  |  |  | 0 | 0 | [28 empty] | #REF!
3 | C | T | 61 | 60_FS_0¦ |  | 44666 |  | 2 |  | u | 1.6.5 | Entrega informe de visitas con outcome de encuestas | NORMAL | Overdue | MANAGER |  |  |  |  | 2022-04-15 | 2022-04-15 | 1 |  |  |  | 0 | 0 | [28 empty] | #REF!
3 | C | T | 34 | 41_FS_0¦ |  | 44657 |  | 2 |  | u | 1.6.6 | Subir resultados y conclusiones en el DASH - arroja zips, insights de audiencia | NORMAL | Overdue | IT |  |  |  |  | 2022-04-06 | 2022-04-07 | 2 |  |  |  | 0 | 0 | [28 empty] | #REF!
3 | SP | T | 52 |  |  |  |  | 1 |  | u | 1.7 | Agenda Paysend | NORMAL | Completed | [5 empty] | 2022-04-19 | 2022-04-21 | 7 |  |  |  | 100 | 1 | [28 empty] | #REF!
3 | C | T | 54 |  |  |  |  | 2 |  | u | 1.7.1 | Revisar flujo de pruebas y montar en el DASH resultados | NORMAL | Completed | MANAGER |  |  |  |  | 2022-04-19 | 2022-04-20 | 2 |  |  |  | 100 | 1 | [28 empty] | #REF!
3 | C | T | 53 |  |  |  |  | 2 |  | u | 1.7.2 | Walktrough de la app | NORMAL | Completed | MANAGER |  |  |  |  | 2022-04-19 | 2022-04-20 | 2 |  |  |  | 100 | 1 | [28 empty] | #REF!
3 | C | T | 55 |  |  |  |  | 2 |  | u | 1.7.3 | Definar fórmula de adquisición | NORMAL | Completed | ESTRATEGIA |  |  |  |  | 2022-04-19 | 2022-04-21 | 3 |  |  |  | 100 | 1 | [28 empty] | #REF!
3 | SP | T | 56 |  |  |  |  | 1 |  | u | 1.8 | Creación | NORMAL | Overdue | [5 empty] | 2022-04-19 | 2022-04-26 | 12 |  |  |  | 0 | 0.5 | [28 empty] | #REF!
3 | C | T | 57 |  |  |  |  | 2 |  | u | 1.8.1 | KV Proyecto | NORMAL | Overdue | CREATIVO |  |  |  |  | 2022-04-19 | 2022-04-26 | 6 |  |  |  | 0 | 0.5 | [28 empty] | #REF!
3 | C | T | 58 |  |  |  |  | 2 |  | u | 1.8.2 | Graficas DASH | NORMAL | Overdue | [5 empty] | 2022-04-19 | 2022-04-26 | 6 |  |  |  | 0 | 0.5 | [28 empty] | #REF!
3 | SP | T | 24 |  |  |  |  | 1 |  | u | 1.9 | Pre-gira y Bootcamp MC - acercamiento a comunidades | NORMAL | Overdue | [5 empty] | 2022-04-20 | 2022-04-28 | 6 |  |  |  | 0 | 0.375 | [28 empty] | #REF!
3 | SP | T | 44 |  |  |  |  | 2 |  | u | 1.9.1 | Pre-gira / | NORMAL | Completed | [5 empty] | 2022-04-20 | 2022-04-20 | 1 |  |  |  | 100 | 1 | [28 empty] | #REF!
3 | C | T | 45 |  |  |  |  | 3 |  | u | 1.9.1.1 | Diseño pregira | NORMAL | Completed | CREATIVO |  |  |  |  | 2022-04-20 | 2022-04-20 | 1 |  |  |  | 100 | 1 | [28 empty] | #REF!
3 | C | T | 51 |  |  |  |  | 2 |  | u | 1.9.2 | Coordinar rutas y contactos .- quién participa, qué se va a hacer | NORMAL | Overdue | MANAGER |  |  |  |  | 2022-04-21 | 2022-04-22 | 2 |  |  |  | 0 | 0.5 | [28 empty] | #REF!
3 | C | T | 50 |  | 62¦ |  |  | 2 |  | u | 1.9.3 | Pre-gira day | NORMAL | Overdue | MANAGER |  |  |  |  | 2022-04-26 | 2022-04-26 | 1 |  |  |  | 0 | 0 | [28 empty] | #REF!
3 | C | T | 62 | 50_FS_0¦ |  | 44678 |  | 2 |  | u | 1.9.4 | Informe de pre-gira - información s/comunidad para diseño de estrategias crear piezas, canales | NORMAL | Overdue | MANAGER |  |  |  |  | 2022-04-27 | 2022-04-28 | 2 |  |  |  | 0 | 0 | [28 empty] | #REF!
3 | SP | T | 46 |  |  |  |  | 1 |  | u | 1.1 | Bootcamp | NORMAL | Planned | [5 empty] | 2022-04-28 | 2022-06-08 | 10 |  |  |  | 0 | 0 | [28 empty] | #REF!
3 | SP | T | 47 |  |  |  |  | 2 |  | u | 1.10.1 | Diseño bootcamp | NORMAL | Planned | [5 empty] | 2022-04-28 | 2022-05-02 | 7 |  |  |  | 0 | 0 | [28 empty] | #REF!
3 | C | T | 18 |  |  |  |  | 3 |  | u | 1.10.1.1 | Produccion bootcamp - locacion - invitados especiales - actividades - agenda que MC quiera desarrollar | NORMAL | Overdue | [5 empty] | 2022-04-28 | 2022-04-29 | 2 |  |  |  | 0 | 0 | [28 empty] | #REF!
3 | C | T | 32 |  |  |  |  | 3 |  | u | 1.10.1.2 | Logística, personal necesario, cómo convocar a la comunidad? | NORMAL | Planned | [5 empty] | 2022-04-28 | 2022-05-02 | 3 |  |  |  | 0 | 0 | [28 empty] | #REF!
3 | C | T | 17 |  |  |  |  | 3 |  | u | 1.10.1.3 | Diseño de herramienta para recopilar información durante el bootcamp | NORMAL | Overdue | [5 empty] | 2022-04-28 | 2022-04-29 | 2 |  |  |  | 0 | 0 | [28 empty] | #REF!
3 | SP | T | 49 |  |  |  |  | 2 |  | u | 1.10.2 | Bootcamp day | NORMAL | Planned | [5 empty] | 2022-06-05 | 2022-06-08 | 3 |  |  |  | 0 | 0 | [28 empty] | #REF!
3 | C | T | 48 |  | 25¦ |  |  | 3 |  | u | 1.10.2.1 | Análisis información obtenida y subida al DASH | NORMAL | Planned | [5 empty] | 2022-06-05 | 2022-06-08 | 3 |  |  |  | 0 | 0 | [28 empty] | #REF!
3 | SP | T | 4 |  |  |  |  | 1 |  | u | 1.11 | Definición estrategia métodos de adquisición - se plantean los escenarios que vamos aprobar - se define campaña digital-activaciones etc | NORMAL | InProgress | [5 empty] | 2022-04-19 | 2022-06-09 | 3 |  |  |  | 0 | 0.33333 | [28 empty] | #REF!
3 | C | T | 25 | 48_FS_0¦ | 8¦27¦20¦11¦10¦22¦ | 44721 |  | 2 |  | u | 1.11.1 | Modelos/escenarios de adquisición a probar | NORMAL | Planned | CREATIVO |  |  |  |  | 2022-06-09 | 2022-06-09 | 1 |  |  |  | 0 | 0 | [28 empty] | #REF!
3 | C | T | 26 |  |  |  |  | 2 |  | u | 1.11.2 | Campaña Digital - canales - mensaje - target - audiencia | NORMAL | Planned | ESTRATEGIA |  |  |  |  | 2022-05-09 | 2022-05-09 | 1 |  |  |  | 0 | 0 | [28 empty] | #REF!
3 | C | T | 63 |  |  |  |  | 2 |  | u | 1.11.3 | Qué tipo de incentivos mortivan ? Validado por consumidores | NORMAL | Completed | ESTRATEGIA |  |  |  |  | 2022-04-19 | 2022-04-19 | 1 |  |  |  | 100 | 1 | [28 empty] | #REF!
3 | C | T | 64 |  |  |  |  | 1 |  | u | 1.12 | aprobación de MC | NORMAL | Completed | [5 empty] | 2022-04-19 | 2022-04-19 | 1 |  |  |  | 100 | 1 | [28 empty] | #REF!
3 | MP | T | 19 |  |  |  |  | 0 |  | u | 2 | PREPARATION | NORMAL | Planned | [5 empty] | 2022-06-10 | 2022-06-16 | 18 |  |  |  | 0 | 0 | [28 empty] | #REF!
3 | C | T | 8 | 25_FS_0¦ |  | 44722 |  | 1 |  | u | 2.1 | Diseño creativos de mensajes (emisores y receptores), piezas, | NORMAL | Planned | [5 empty] | 2022-06-10 | 2022-06-15 | 4 |  |  |  | 0 | 0 | [28 empty] | #REF!
3 | C | T | 27 | 25_FS_0¦ |  | 44722 |  | 1 |  | u | 2.2 | Diseño plan de incentivos consumidores/agencias/receptores | NORMAL | Planned | [5 empty] | 2022-06-10 | 2022-06-15 | 4 |  |  |  | 0 | 0 | [28 empty] | #REF!
3 | C | T | 20 | 25_FS_0¦ |  | 44722 |  | 1 |  | u | 2.3 | Producción de digitales/piezas/uniformes/regalos | NORMAL | Planned | [5 empty] | 2022-06-10 | 2022-06-16 | 5 |  |  |  | 0 | 0 | [28 empty] | #REF!
3 | C | T | 11 | 25_FS_0¦ |  | 44722 |  | 1 |  | u | 2.4 | Acceso a plataformas Paysend | NORMAL | Planned | [5 empty] | 2022-06-10 | 2022-06-13 | 2 |  |  |  | 0 | 0 | [28 empty] | #REF!
3 | C | T | 10 | 25_FS_0¦ |  | 44722 |  | 1 |  | u | 2.5 | Comunicación al consumidor impresión/digital | NORMAL | Planned | [5 empty] | 2022-06-10 | 2022-06-13 | 2 |  |  |  | 0 | 0 | [28 empty] | #REF!
3 | C | T | 22 | 25_FS_0¦ |  | 44722 |  | 1 |  | u | 2.6 | Preparación DASH internamente | NORMAL | Planned | [5 empty] | 2022-06-10 | 2022-06-10 | 1 |  |  |  | 0 | 0 | [28 empty] | #REF!
3 | MP | T | 28 |  |  |  |  | 0 |  | u | 3 | EJECUCIÓN | NORMAL | InProgress | [5 empty] | 2022-04-22 | 2022-07-27 | 49 |  |  |  | 0 | 0.25 | [28 empty] | #REF!
3 | C | T | 29 |  |  |  |  | 1 |  | u | 3.1 | Itinerario de visitas/activaciones | NORMAL | Planned | [5 empty] | 2022-06-06 | 2022-06-07 | 2 |  |  |  | 0 | 0 | [28 empty] | #REF!
3 | C | T | 9 |  | 12¦ |  |  | 1 |  | u | 3.2 | Speach entrenamiento team y herramienta que van a utilizar | NORMAL | Planned | [5 empty] | 2022-05-20 | 2022-05-26 | 5 |  |  |  | 0 | 0 | [28 empty] | #REF!
3 | C | T | 21 |  |  |  |  | 1 |  | u | 3.3 | Entrenamiento de embajadores | NORMAL | Completed | [5 empty] | 2022-04-22 | 2022-04-25 | 2 |  |  |  | 100 | 1 | [28 empty] | #REF!
3 | C | T | 30 |  |  |  |  | 1 |  | u | 3.4 | Team en calle | NORMAL | Planned | [5 empty] | 2022-06-02 | 2022-07-27 | 40 |  |  |  | 0 | 0 | [28 empty] | #REF!
3 | MP | T | 5 |  |  |  |  | 0 |  | u | 4 | XXXXX | NORMAL | InProgress | [5 empty] | 2022-03-30 | 2022-05-27 | 3 |  |  |  | 0 | 0.66667 | [28 empty] | #REF!
3 | C | T | 6 |  |  |  |  | 1 |  | u | 4.1 | xxx | NORMAL | Completed | [5 empty] | 2022-04-22 | 2022-04-22 | 1 |  |  |  | 100 | 1 | [28 empty] | #REF!
3 | C | T | 7 |  |  |  |  | 1 |  | u | 4.2 | xxx | NORMAL | Completed | [5 empty] | 2022-03-30 | 2022-03-30 | 1 |  |  |  | 100 | 1 | [28 empty] | #REF!
3 | C | T | 12 | 9_FS_0¦ |  | 44708 |  | 1 |  | u | 4.3 | xxx | NORMAL | Planned | [5 empty] | 2022-05-27 | 2022-05-27 | 1 |  |  |  | 0 | 0 | [28 empty] | #REF!
3 | T | T | 13 |  |  |  |  | 0 |  | u | 5 | xxx | NORMAL | Completed | [5 empty] | 2022-03-30 | 2022-03-30 | 1 |  |  |  | 100 | 1 | [28 empty] | #REF!
11 | MP | T | 1 |  |  |  |  | 0 |  | u | 1 | PRE PURCHASE STAGE | NORMAL | Overdue |  |  | 2022-03-10 | 2022-03-10 |  | 2022-03-04 | 2022-04-27 | 30 |  |  |  | 0 | 0.21429 | 2022-03-09 | 2022-03-09 | [26 empty] | #REF!
11 | C | T | 57 |  |  |  |  | 1 |  | u | 1.1 | dgdg | NORMAL | Overdue | [5 empty] | 2022-03-22 | 2022-03-31 | 10 |  |  |  | 0 | 0.5 | [28 empty] | #REF!
11 | C | T | 61 |  |  |  |  | 1 |  | u | 1.2 | dgdg | NORMAL | Overdue | [5 empty] | 2022-03-10 | 2022-03-19 | 10 |  |  |  | 0 | 0.5 | [28 empty] | #REF!
11 | C | T | 60 |  |  |  |  | 1 |  | u | 1.3 | dgdg | NORMAL | Overdue | [5 empty] | 2022-04-18 | 2022-04-27 | 10 |  |  |  | 0 | 0.5 | [28 empty] | #REF!
11 | M | M | 51 |  |  |  |  | 1 |  | u | 1.4 | Development Site identified (3 Apple Flat Rd, Alligator Creek) | NORMAL | Overdue |  |  | 2022-03-10 | 2022-03-10 | 0 | 2022-03-17 | 2022-03-17 | 0 |  |  |  | 0 | 0 | 2022-03-09 | 2022-03-09 | 0 |  |  |  | 3 Apple Flat Rd, Alligator Creek | [21 empty] | #REF!
11 | M | M | 55 |  |  |  |  | 1 |  | u | 1.5 | Development Site identified (3 Apple Flat Rd, Alligator Creek) | NORMAL | Overdue | [5 empty] | 2022-03-04 | 2022-03-04 | 0 |  |  |  | 0 | 0 | [6 empty] | 3 Apple Flat Rd, Alligator Creek | [21 empty] | #REF!
11 | M | M | 54 |  |  |  |  | 1 |  | u | 1.6 | Development Site identified (3 Apple Flat Rd, Alligator Creek) | NORMAL | Overdue | [5 empty] | 2022-03-06 | 2022-03-06 | 0 |  |  |  | 0 | 0 | [6 empty] | 3 Apple Flat Rd, Alligator Creek | [21 empty] | #REF!
11 | M | M | 56 |  |  |  |  | 1 |  | u | 1.7 | Development Site identified (3 Apple Flat Rd, Alligator Creek) | NORMAL | Overdue | [5 empty] | 2022-03-04 | 2022-03-04 | 0 |  |  |  | 0 | 0 | [6 empty] | 3 Apple Flat Rd, Alligator Creek | [21 empty] | #REF!
11 | MP | T | 2 |  |  |  |  | 0 |  | u | 2 | NEGOTIATING CONTRACTS & PURCHASING | NORMAL | InProgress | [5 empty] | 2022-03-04 | 2022-07-01 | 1 |  |  |  | 0 | 0.33333 | 2022-04-12 | 2022-04-12 |  |  | 25000 | 5000 | [22 empty] | #REF!
11 | SP | T | 52 |  |  |  |  | 1 |  | u | 2.1 | PRIOR TO EXECUTION STAGE | NORMAL | Completed | [5 empty] | 2022-03-04 | 2022-03-07 | 0 |  |  |  | 100 | 1 | 2022-04-12 | 2022-04-12 | [26 empty] | #REF!
11 | M | M | 34 |  | 35¦ |  |  | 2 |  | u | 2.1.1 | Form 6 - Enlist Buyers Agent (Ben Waugh) | NORMAL | Completed | [5 empty] | 2022-03-04 | 2022-03-04 | 0 |  |  |  | 100 | 1 | [6 empty] | Ben Waugh | [21 empty] | #REF!
11 | M | M | 35 | 34_FS_0¦ | 36¦ | 44625 |  | 2 |  | u | 2.1.2 | Sign Contract | NORMAL | Completed | [5 empty] | 2022-03-05 | 2022-03-05 | 0 |  |  |  | 100 | 1 | 2022-04-12 | 2022-04-12 | 0 | [25 empty] | #REF!
11 | M | M | 36 | 35_FS_0¦ | 37¦ | 44626 |  | 2 |  | u | 2.1.3 | Select Solicitor | NORMAL | Completed | [5 empty] | 2022-03-06 | 2022-03-06 | 0 |  |  |  | 100 | 1 | [6 empty] | Use QPLG, Yasmin Parker | [21 empty] | #REF!
11 | M | M | 37 | 36_FS_0¦ | 45¦46¦ | 44627 |  | 2 |  | u | 2.1.4 | Finalise Contract (both sides signed and accepted) agreed $593,000 | NORMAL | Completed | [5 empty] | 2022-03-07 | 2022-03-07 | 0 |  |  |  | 100 | 1 | [6 empty] | Agreed price $593K Contract is now binding but subject to key conditions being met | [21 empty] | #REF!
11 | SP | T | 53 |  |  |  |  | 1 |  | u | 2.2 | AFTER CONTRACT EXECUTED STAGE (Contract is subject to key conditions) | NORMAL | Completed | [5 empty] | 2022-03-10 | 2022-03-10 | 0 |  |  |  | 100 | 1 |  |  |  |  | 5000 | 5000 | [22 empty] | #REF!
11 | M | M | 45 | 37_FS_2¦ |  | 44630 |  | 2 |  | u | 2.2.1 | Pay $5K Deposit (within 2D of contract date) | NORMAL | Completed | [5 empty] | 2022-03-10 | 2022-03-10 | 0 |  |  |  | 100 | 1 |  |  |  |  | 5000 | 5000 | Don't forget to pay your $5K deposit (within 2 days of contract date) | [21 empty] | #REF!
11 | M | M | 46 | 37_FS_28¦ |  | 44656 |  | 1 |  | u | 2.3 | Engage Town Planner (straight after contract date) | NORMAL | Completed | [5 empty] | 2022-04-05 | 2022-04-05 | 0 |  |  |  | 100 | 1 | [6 empty] | Before 28 days is up get your building and pest done. (just to make sure no structural building issues or live termites). Twin Cities Bldg and Pest (Phone No: 07 4723 2770) - | [21 empty] | #REF!
11 | M | M | 44 |  |  |  |  | 1 |  | u | 2.4 | Complete Building Pest Inspection (before 28D) | NORMAL | Planned | [5 empty] | 2022-07-01 | 2022-07-01 | 0 |  |  |  | 0 | 0 | [6 empty] | Use Twin Cities Bldg and Pest Ph: 07 4723 2770. Make sure no structural building issues or live termites. | [21 empty] | #REF!
11 | M | M | 43 |  |  |  |  | 1 |  | u | 2.5 | Advise 'unconditional' to Solicitor | NORMAL | Overdue | [5 empty] | 2022-04-01 | 2022-04-01 | 0 |  |  |  | 0 | 0 | [6 empty] | This means all checks are done and MITR happy to proceed with the deal and the contract terms are now satisfied. | [21 empty] | #REF!
11 | M | M | 42 |  |  |  |  | 1 |  | u | 2.6 | Pay $20K balance (within 35D of contract date) | NORMAL | Planned | [5 empty] | 2022-07-01 | 2022-07-01 | 0 |  |  |  | 0 | 0 |  |  |  |  | 20000 | [23 empty] | #REF!
11 | M | M | 38 |  |  |  |  | 1 |  | u | 2.7 | Contract Unconditional within 35D (terms and condition satified) | NORMAL | Planned | [5 empty] | 2022-06-01 | 2022-06-01 | 0 |  |  |  | 0 | 0 | [28 empty] | #REF!
11 | M | M | 40 |  |  |  |  | 1 |  | u | 2.8 | Pay Buyers Agent Commission | NORMAL | Planned | [5 empty] | 2022-07-01 | 2022-07-01 | 0 |  |  |  | 0 | 0 | [28 empty] | #REF!
11 | C | T | 41 |  |  |  |  | 1 |  | u | 2.9 | Proceed with steps as recommended by Town Planner to DA into Council | NORMAL | Overdue | [5 empty] | 2022-04-01 | 2022-04-01 | 1 |  |  |  | 0 | 0 | [28 empty] | #REF!
11 | MP | T | 5 |  |  |  |  | 0 |  | u | 3 | DEVELOPMENT | NORMAL | Planned | [5 empty] | 2022-01-01 | 2022-08-01 | 5 |  |  |  | 0 | 0 | [28 empty] | #REF!
11 | M | M | 49 |  |  |  |  | 1 |  | u | 3.1 | Submit DA to Council and Approval Stage | NORMAL | Overdue | [5 empty] | 2022-04-01 | 2022-04-01 | 0 |  |  |  | 0 | 0 | [28 empty] | #REF!
11 | M | M | 48 |  |  |  |  | 1 |  | u | 3.2 | Survey | NORMAL | Planned | [5 empty] | 2022-08-01 | 2022-08-01 | 0 |  |  |  | 0 | 0 | [28 empty] | #REF!
11 | M | M | 47 |  |  |  |  | 1 |  | u | 3.3 | Power Application | NORMAL | Overdue | [5 empty] | 2022-04-01 | 2022-04-01 | 0 |  |  |  | 0 | 0 | [28 empty] | #REF!
11 | C | T | 3 |  | 64¦ |  |  | 1 |  | u | 3.4 | Operational Work Stage (if time permits or do after settlement) | NORMAL | Overdue | [5 empty] | 2022-04-01 | 2022-04-05 | 5 |  |  |  | 0 | 0 | [28 empty] | #REF!
11 | M | M | 50 |  |  |  |  | 1 |  | u | 3.5 | Settle Property as per Contract Timing | NORMAL | Overdue | [5 empty] | 2022-01-01 | 2022-01-01 | 0 |  |  |  | 0 | 0 | [28 empty] | #REF!
11 | MP | T | 7 |  |  |  |  | 0 |  | u | 4 | COMPLETION | NORMAL | Overdue | [5 empty] | 2022-04-01 | 2022-04-07 | 7 |  |  |  | 0 | 0 | [28 empty] | #REF!
11 | C | T | 15 |  | 65¦ |  |  | 1 |  | u | 4.1 | d | NORMAL | Overdue | [5 empty] | 2022-04-01 | 2022-04-03 | 3 |  |  |  | 0 | 0 | [28 empty] | #REF!
11 | C | T | 65 | 15_FS_0¦ |  | 44655 |  | 1 |  | u | 4.2 | d | NORMAL | Overdue | [5 empty] | 2022-04-04 | 2022-04-04 | 1 |  |  |  | 0 | 0 | [28 empty] | #REF!
11 | C | T | 64 | 3_FS_0¦ | 63¦ | 44657 |  | 1 |  | u | 4.3 | d | NORMAL | Overdue | [5 empty] | 2022-04-06 | 2022-04-06 | 1 |  |  |  | 0 | 0 | [28 empty] | #REF!
11 | C | T | 63 | 64_SS_0¦ | 62¦ | 44657 |  | 1 |  | u | 4.4 | d | NORMAL | Overdue | [5 empty] | 2022-04-06 | 2022-04-06 | 1 |  |  |  | 0 | 0 | [28 empty] | #REF!
11 | C | T | 62 | 63_FS_0¦ |  | 44658 |  | 1 |  | u | 4.5 | d | NORMAL | Overdue | [5 empty] | 2022-04-07 | 2022-04-07 | 1 |  |  |  | 0 | 0 | [28 empty] | #REF!
12 | T | T | 4 |  | 2¦ |  |  | 0 |  | u | 1 | Type here or double click to edit in form | NORMAL | Planned | [5 empty] | 2022-05-03 12:00 | 2022-05-11 12:00 | 54 |  |  |  | 0 | 0 | [28 empty] | #REF!
12 | T | T | 7 |  | 6¦5¦ |  |  | 0 |  | u | 2 | Type here or double click to edit in form | NORMAL | Planned | [5 empty] | 2022-05-02 15:00 | 2022-05-03 18:00 | 12 |  |  |  | 0 | 0 | [28 empty] | #REF!
12 | T | T | 6 | 7_FS_2¦ |  | 44685.4583 |  | 0 |  | u | 3 | Type here or double click to edit in form | NORMAL | Planned | [5 empty] | 2022-05-04 11:00 | 2022-05-05 10:00 | 8 |  |  |  | 0 | 0 | [28 empty] | #REF!
12 | T | T | 5 | 7_FS_24¦ |  | 44687.625 |  | 0 |  | u | 4 | Type here or double click to edit in form | NORMAL | Planned | [5 empty] | 2022-05-06 15:00 | 2022-05-17 15:00 | 63 |  |  |  | 0 | 0 | [28 empty] | #REF!
12 | T | T | 1 | 3_FS_0¦ |  | 44697.375 |  | 0 |  | u | 5 | Type here or double click to edit in form | NORMAL | Planned | [5 empty] | 2022-05-16 09:00 | 2022-05-16 15:00 | 6 |  |  |  | 0 | 0 | [28 empty] | #REF!
12 | T | T | 3 |  | 1¦ |  |  | 0 |  | u | 6 | Type here or double click to edit in form | NORMAL | Planned | [5 empty] | 2022-05-06 09:00 | 2022-05-13 18:00 | 54 |  |  |  | 0 | 0 | [28 empty] | #REF!
12 | T | T | 2 | 4_SS_0¦ | 10¦ | 44684.5 |  | 0 |  | u | 7 | Type here or double click to edit in form | NORMAL | Planned | [5 empty] | 2022-05-03 12:00 | 2022-05-06 18:00 | 33 |  |  |  | 0 | 0 | [28 empty] | #REF!
12 | T | T | 10 | 2_FS_0¦ | 11¦ | 44690.375 |  | 0 |  | u | 8 | Type here or double click to edit in form | NORMAL | Planned | [5 empty] | 2022-05-09 09:00 | 2022-05-12 15:00 | 33 |  |  |  | 0 | 0 | [28 empty] | #REF!
12 | T | T | 11 | 10_FF_0¦ | 12¦ |  | 44693.625 | 0 |  | u | 9 | Type here or double click to edit in form | NORMAL | Planned | [5 empty] | 2022-05-09 09:00 | 2022-05-12 15:00 | 33 |  |  |  | 0 | 0 | [28 empty] | #REF!
12 | T | T | 12 | 11_SF_0¦ |  |  | 44690.375 | 0 |  | u | 10 | Type here or double click to edit in form | NORMAL | Planned | [5 empty] | 2022-05-03 12:00 | 2022-05-09 09:00 | 33 |  |  |  | 0 | 0 | [28 empty] | #REF!
Please DO NOT delete this worksheet. Deleting this Worksheet will result in errors.

## GanttDashboardTemplate (hidden)
|  |  | Project ID | Project Worksheet | Project Name | Lead | Project Completion | ESTIMATED BUDGET | BASELINE | BASELINE | ESTIMATED | ACTUAL | Currency | Earliest Start Date | Earliest End Date | Total Tasks | Completed Tasks | In-Progress Tasks | Planned Tasks | Overdue Tasks | Low | Normal | High | Est Budget | Act Costs |  | % Comp | Remaining | % Over Budget
|  |  | S | Selected Project | Selected Project |  | 0.5 | 1000 | 2000 | 200 | 100 | 500 | $ | 2021-07-21 | 2021-08-03 | 5 | 0 | 0 | 5 | 0 |  |  |  | $ 1000 | $ 500 | In-Progress | 50% | 50% | -50%
PROJECT SUMMARY |  |  | 0 | All Projects | All Projects |  | 0 | 1000 | 2000 | 200 | 100 | 300 | $ | 2021-07-21 | 2021-08-03 | 5 | 0 | 0 | 5 | 0
| Project Status | In-Progress | 1 | Project Plan | Project Name - Click to Edit | Click to edit | 0 | 1000 | 2000 | 200 | 100 | 300 | $ | 2021-07-21 | 2021-08-03 | 5 | 0 | 0 | 5 | 0
Lead
| Start Date | 2021-07-21
| End Date | 2021-08-03
| Total Tasks | 5
| Completed | 0
| In-Progress | 0
| Planned | 5
| Overdue | 0
ESTIMATED BUDGET
$ 1000
$ 500
ACTUAL COST
50%
Refresh
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
COMPLETE
Timeline: Works in Excel 2013 or higher. Do not move or resize.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
Please DO NOT delete this worksheet. Deleting this Worksheet will result in errors.

## GanttSettingsTemplate (hidden)
GCTYPE | SSN | DateFormat | WeekNumType | EC | CurrencySymbol | BaselineBudget | EstimatedBudget | ActualCosts | TotalACS | ShowOverdueBar | ShowPercBar | ShowPercDataBar | ShowBaselineBar | ShowActualBar | ShowCompleted | ShowInProgress | ShowPlanned | ShowLate | ShowTimelineGrid | HiliteHolidays | HiliteWorkOffDays | HiliteHolidaysPR | HiliteWorkOffDaysPR | ShowTodayLines | ShowDependencyConnector | ShowGrouping | ShowEstBaseBar | CurrentView | WeekStartDay | EnableBarText | BarTextCharacters | BarTextFontSize | BarTextDataColumnName | BarTextIsBold | BarTextIsItalic | BarTextIsUnderline | PercentageEntryMode | PercentageCalculationType | ProjectName | ThemeName | SelectedTheme | EBC | EMC | PBC | PDC | BBC | ABC | OBC | DLC | TLC | TBC | GBC | PRC | HBC | HC | WC | HCPR | WCPR | CR1C | CR12C | CR2C | CR3C | TGB | EBaseC | TPCH | TPCN | TPCL | TSCC | TSCI | TSCP | HCOL | DCOL | WCOL | MCOL | QCOL | HYCOL | YCOL | HWID | DWID | WWID | MWID | QWID | HYWID | YWID | RCCal | PTRC | TSD | TED | GRT | RefreshTimeline | TimelineVisible | CalcBED | CalcAED | PTDS | csYear | ceYear | csDate | ceDate | SavedDate | HideHolidays | HideWorkOffDays | HideNonWorkingHours | VerticalBorders | LockWB | Campaign | LV | LiType | peru | chirun | vidud | liky | duli | FiSa
ds082 | 1 | DDD DD\-MMM\-YY | ISO | TRUE | $ | 20000 | 10000 |  | 0 | FALSE | TRUE | TRUE | TRUE | TRUE | 1 | 1 | 1 | 1 | TRUE | TRUE | TRUE | FALSE | FALSE | TRUE | FALSE | 0 | 1 | D | 1 | FALSE | 20 | 9 | Task | TRUE | FALSE | FALSE | manual | simple |  | Blue | Classic | [29 empty] | 56 | 35 | 6 | 2 | 2 | 3 | 2 | 3 | 3 | 6 | 8 | 10 | 12 | 15 | TRUE | TRUE | 2019-07-01 | 2019-08-02 | resourcesettings | TRUE | TRUE | TRUE | TRUE | TRUE | 2000 | 2050 | 2000-01-01 | 2050-01-01 | 2024-10-30 | FALSE | FALSE | FALSE | TRUE | TRUE | Cpc | 1 | T42VP | Milenka Cuzi Cruz | 3123685277407492856894864013771059744140 | TR8%{/QM | N4fL3sgyYf-Gm2xds9E-6dG7b72mevs |  | 2024-10-30
Classic
Excel
Dark
Custom
Please DO NOT delete this worksheet. Deleting this Worksheet will result in errors.

## PivotSheet (hidden)
ProjectFilter | TRUE | ProjectFilter | TRUE | ProjectFilter | (Multiple Items) | ProjectFilter | (Multiple Items) | ProjectFilter | (Multiple Items) | ProjectFilter | (Multiple Items) | ProjectFilter | (Multiple Items) | ProjectFilter | (Multiple Items)
dType | (Multiple Items) | dType | (Multiple Items) | dType | (Multiple Items) | GEType | (Multiple Items) | dType | (Multiple Items) | dType | (Multiple Items) | dType | (Multiple Items) | dType | (Multiple Items)
Row Labels | Count of tID | Row Labels | Count of tID | Values |  |  |  | Row Labels | Count of tID | Row Labels
Overdue | 10 | NORMAL | 10 | Baseline Cost |  |  |  | 7-Mar | 1 | (blank)
|  |  |  | Estimated Cost | 25000 |  |  | 18-Mar | 1
|  |  |  | Actual Cost | 5000 |  |  | 1-Apr | 8
Please DO NOT delete this worksheet. Deleting this Worksheet will result in errors.

## Certificados
GEType | TID | Dependency | Dependents | StartConstrain | EndConstrain | TIL | SS | TaskIcon | WBS | Task | Priority | Status | Resource | ResourceCost | BSD | BED | BD | ESD | EED | ED | WBSPredecessors | WBSSuccessors | Work | Done | PercentageCompleted | ASD | AED | AD | BCS | ECS | ACS | Notes | TColor | TPColor | BLColor | ACColor | Custom 1 | Custom 2 | Custom 3 | Custom 4 | Custom 5 | Custom 6 | Custom 7 | Custom 8 | Custom 9 | Custom 10 | Custom 11 | Custom 12 | Custom 13 | Custom 14 | Custom 15 | Custom 16 | Custom 17 | Custom 18 | Custom 19 | Custom 20 | ShapeInfoE | ShapeInfoB | ShapeInfoA | LC | TimelineStart | [33 empty] | TimelineEnd | LLC
System | System | System | System | System | System | System | 1¦GS1¦RS1 | System | System | System | System | System | System | System | System | System | System | System | System | System | System | System | System | System | System | System | System | System | System | System | System | System | System | System | System | System | Custom 1 | Custom 2 | Custom 3 | Custom 4 | Custom 5 | Custom 6 | Custom 7 | Custom 8 | Custom 9 | Custom 10 | Custom 11 | Custom 12 | Custom 13 | Custom 14 | Custom 15 | Custom 16 | Custom 17 | Custom 18 | Custom 19 | Custom 20 | System | System | System | System
[9 empty] | generador de certificados | [50 empty] | S_TE_1 | 45593 | 45594 | 45595 | 45596 | 45597 | 45598 | 45599 | 45600 | 45601 | 45602 | 45603 | 45604 | 45605 | 45606 | 45607 | 45608 | 45609 | 45610 | 45611 | 45612 | 45613 | 45614 | 45615 | 45616 | 45617 | 45618 | 45619 | 45620 | 45621 | 45622 | 45623 | 45624 | 45625 | 45626 | 45627
[9 empty] | Project Lead: | [50 empty] | System 45593: W44; System 45600: W45; System 45607: W46; System 45614: W47; System 45621: W48
[9 empty] | Project Budget: Estimated: $0,00 ¦ Baseline: $0,00 ¦ Task Costs: Estimated: $0,00 ¦ Baseline: $0,00 ¦ Actual: $0,00 | [51 empty] | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1
GEType | TID | Dependency | Dependents | StartConstrain | EndConstrain |  |  |  | WBS | Task | Priority | Status | Resource | Resource Cost | Baseline Start | Baseline End | Baseline Duration | Start | Finish | Duration | WBS Predecessors | WBS Successors | Work | Done | % Complete | Actual Start | Actual End | Actual Duration | Baseline Cost | Est. Cost | Actual Cost | Notes | Bar Color | % Color | Baseline Color | Actual Color | Custom 1 | Custom 2 | Custom 3 | Custom 4 | Custom 5 | Custom 6 | Custom 7 | Custom 8 | Custom 9 | Custom 10 | Custom 11 | Custom 12 | Custom 13 | Custom 14 | Custom 15 | Custom 16 | Custom 17 | Custom 18 | Custom 19 | Custom 20 | ShapeInfoE | ShapeInfoB | ShapeInfoA |  | l | m | m | j | v | s | d | l | m | m | j | v | s | d | l | m | m | j | v | s | d | l | m | m | j | v | s | d | l | m | m | j | v | s | d
T | 15 |  |  |  |  | 0 |  | u | 1 | Dimplomas_Certificados_v1 | NORMAL | Planned | [5 empty] | 2024-10-30 | 2024-10-30 | 1 |  |  |  | 0 | 0% | [31 empty] | S_TE¦15¦1585¦87,1¦1622¦99
T | 1 | 3_FS_0¦ |  | 45596 |  | 0 |  | u | 2 | Panel de usuario | NORMAL | Planned | [5 empty] | 2024-10-31 | 2024-11-07 | 6 | 3 FS 0¦ |  |  | 0 | 0% | [31 empty] | S_TE¦1¦1624¦105,1¦1934¦117
T | 4 |  |  |  |  | 0 |  | u | 3 | Home | LOW | Planned | [5 empty] | 2024-10-30 | 2024-10-31 | 2 |  |  |  | 0 | 0% | [31 empty] | S_TE¦4¦1585¦123,1¦1661¦135
T | 3 |  | 1¦ |  |  | 0 |  | u | 4 | Acceso Usuario | NORMAL | Planned | [5 empty] | 2024-10-30 | 2024-10-30 | 1 |  | 1¦ |  | 0 | 0% | [31 empty] | S_TE¦3¦1585¦141,1¦1622¦153
T | 5 |  |  |  |  | 0 |  | u | 5 | Mis Cursos | HIGH | Planned | [5 empty] | 2024-10-30 | 2024-11-04 | 4 |  |  |  | 0 | 0% | [31 empty] | S_TE¦5¦1585¦159,1¦1817¦171
T | 6 |  |  |  |  | 0 |  | u | 6 | Ver Certificado | NORMAL | Planned | [5 empty] | 2024-10-30 | 2024-10-31 | 2 |  |  |  | 0 | 0% | [31 empty] | S_TE¦6¦1585¦177,1¦1661¦189
T | 7 |  |  |  |  | 0 |  | u | 7 | Perfil | NORMAL | Planned | [5 empty] | 2024-10-30 | 2024-11-01 | 3 |  |  |  | 0 | 0% | [31 empty] | S_TE¦7¦1585¦195,1¦1700¦207
T | 2 |  |  |  |  | 0 |  | u | 8 | Panel de administrador | NORMAL | Planned | [5 empty] | 2024-10-31 | 2024-10-31 | 1 |  |  |  | 0 | 0% | [31 empty] | S_TE¦2¦1624¦213,1¦1661¦225
T | 8 |  |  |  |  | 0 |  | u | 9 | Acceso a Administrador | NORMAL | Planned | [5 empty] | 2024-10-30 | 2024-10-30 | 1 |  |  |  | 0 | 0% | [31 empty] | S_TE¦8¦1585¦231,1¦1622¦243
T | 9 |  |  |  |  | 0 |  | u | 10 | Mantenimiento de Cursos | NORMAL | Planned | [5 empty] | 2024-10-30 | 2024-11-06 | 6 |  |  |  | 0 | 0% | [31 empty] | S_TE¦9¦1585¦249,1¦1895¦261
T | 10 |  |  |  |  | 0 |  | u | 11 | Mantenimiento de Categorias | NORMAL | Planned | [5 empty] | 2024-10-30 | 2024-11-05 | 5 |  |  |  | 0 | 0% | [31 empty] | S_TE¦10¦1585¦267,1¦1856¦279
T | 11 |  |  |  |  | 0 |  | u | 12 | mantenimientos de Instructivos | NORMAL | Planned | [5 empty] | 2024-10-30 | 2024-11-07 | 7 |  |  |  | 0 | 0% | [31 empty] | S_TE¦11¦1585¦285,1¦1934¦297
T | 12 |  |  |  |  | 0 |  | u | 13 | Mantenimientos de Usuarios | NORMAL | Planned | [5 empty] | 2024-10-30 | 2024-11-04 | 4 |  |  |  | 0 | 0% | [31 empty] | S_TE¦12¦1585¦303,1¦1817¦315
T | 13 |  |  |  |  | 0 |  | u | 14 | Detalle de Certificado | NORMAL | Planned | [5 empty] | 2024-10-30 | 2024-10-31 | 2 |  |  |  | 0 | 0% | [31 empty] | S_TE¦13¦1585¦321,1¦1661¦333
T | 14 |  |  |  |  | 0 |  | u | 15 | Perfil | NORMAL | Planned | [5 empty] | 2024-10-30 | 2024-10-30 | 1 |  |  |  | 0 | 0% | [31 empty] | S_TE¦14¦1585¦339,1¦1622¦351
Type here to add a new task
generador de certificados
octubre-2024
noviembre-2024
dic-24
Dimplomas_Certificad
Panel de usuario
Home
Acceso Usuario
Mis Cursos
Ver Certificado
Perfil
Panel de administrad
Acceso a Administrad
Mantenimiento de Cur
Please upgrade to the Pro version.
Please upgrade to the Pro version.
Please upgrade to the Pro version.
Please upgrade to the Pro version.
Please upgrade to the Pro version.

## Help
[5 empty] | asdflkjl | ;J=,F\)-'+%tyzivm":YHs
Gantt Excel - Project Management in Excel
cpc
For Windows Excel versions 2007 - 2021 + All versions of Microsoft 365 and MAC Excel Version 2016 - 2021 + All versions of Microsoft 365
QUICK GUIDE
1 | 1 | Enable Macros
Click here for help to Enable Macros
2 |  | Use the Gantt Menu tab in the Excel Ribbon to Create, View and Edit Gantt Charts
Quick Start Guide
CLICK HERE FOR DOCUMENTATION

## RS1 (hidden)
Resource | Cost | Use Org Holidays | Department |  | Workhours Start | Workhours End | WorkdaySun | WorkdayMon | WorkdayTue | WorkdayWed | WorkdayThu | WorkdayFri | WorkdaySat | Holidays
Organization |  | FALSE |  | DO NOT MODIFY THIS SHEET OR INSERT COLUMNS | 9:00 | 18:00 | 0 | 1 | 1 | 1 | 1 | 1 | 0

## GS1 (hidden)
GCTYPE | SSN | DateFormat | WeekNumType | EC | CurrencySymbol | BaselineBudget | EstimatedBudget | ActualCosts | TotalACS | ShowOverdueBar | ShowPercBar | ShowPercDataBar | ShowBaselineBar | ShowActualBar | ShowCompleted | ShowInProgress | ShowPlanned | ShowLate | ShowTimelineGrid | HiliteHolidays | HiliteWorkOffDays | HiliteHolidaysPR | HiliteWorkOffDaysPR | ShowTodayLines | ShowDependencyConnector | ShowGrouping | ShowEstBaseBar | CurrentView | WeekStartDay | EnableBarText | BarTextCharacters | BarTextFontSize | BarTextDataColumnName | BarTextIsBold | BarTextIsItalic | BarTextIsUnderline | PercentageEntryMode | PercentageCalculationType | ProjectName | ThemeName | SelectedTheme | EBC | EMC | PBC | PDC | BBC | ABC | OBC | DLC | TLC | TBC | GBC | PRC | HBC | HC | WC | HCPR | WCPR | CR1C | CR12C | CR2C | CR3C | TGB | EBaseC | TPCH | TPCN | TPCL | TSCC | TSCI | TSCP | HCOL | DCOL | WCOL | MCOL | QCOL | HYCOL | YCOL | HWID | DWID | WWID | MWID | QWID | HYWID | YWID | RCCal | PTRC | TSD | TED | GRT | RefreshTimeline | TimelineVisible | CalcBED | CalcAED | PTDS | csYear | ceYear | csDate | ceDate | SavedDate | HideHolidays | HideWorkOffDays | HideNonWorkingHours | VerticalBorders | LockWB | Campaign
ds082 | 1 | DDD DD\-MMM\-YY | ISO | TRUE | $ | 0 | 0 |  | 0 | FALSE | TRUE | TRUE | TRUE | TRUE | 1 | 1 | 1 | 1 | TRUE | TRUE | TRUE | FALSE | FALSE | TRUE | FALSE | 0 | 1 | D | 1 | TRUE | 20 | 9 | Task | TRUE | FALSE | FALSE | manual | simple |  | Blue | Classic | [29 empty] | 480 | 34 | 4 | 2 | 1 | 1 | 1 | 3 | 3 | 6 | 8 | 10 | 12 | 15 | TRUE | TRUE | 2024-10-28 | 2024-12-01 | RS1 | TRUE | TRUE | TRUE | TRUE | TRUE | 2000 | 2050 | 2000-01-01 | 2050-01-01 | 2023-02-08 | FALSE | FALSE | FALSE | TRUE | TRUE | Cpc
Classic
Excel
Dark
Custom